## Project schedule
| CIVE 202 Project #3 | [5 empty] | Project start: | [7 empty] | 2026-02-26
| VanArsdel, Ltd. | Eddie Vargas |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-02-23 to 2026-04-19
 | time axis 2026-02-23 to 2026-04-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning for function development
| Project Planning Gantt Chart | Eddie Vargas | 100% | 2026-02-26 | 2026-03-28 | 31
| Calculate Mix Designs | Eddie Vargas | 100% | 2026-03-03 | 2026-03-31 | 29
Draft functions in Python
| Problem #1 Translate Excel Logic Python | Eddie Vargas | 100% | 2026-03-03 | 2026-03-31 | 29
| Problem #2 Sequencial User Prompts | Eddie Vargas | 100% | 2026-03-03 | 2026-03-31 | 29
| Problem #3 Calculate Mix Designs | Eddie Vargas | 100% | 2026-03-03 | 2026-03-31 | 29
Execution
| Data Cleaning | Eddie Vargas | 100% | 2026-03-08 | 2026-03-31 | 24
| Testing and Validation | Eddie Vargas | 100% | 2026-03-08 | 2026-03-31 | 24
| ACD | Eddie Vargas | 100% | 2026-03-08 | 2026-03-31 | 24
| Technical Report | Eddie Vargas | 100% | 2026-03-08 | 2026-03-31 | 24
| SOW | Eddie Vargas | 100% | 2026-03-08 | 2026-03-31 | 24
Evaluation
| Monitor progress | Eddie Vargas | 100% | 2026-03-13 | 2026-03-31 | 19
| Evaluate progress | Eddie Vargas | 100% | 2026-03-13 | 2026-03-31 | 19
| Gather feedback | Eddie Vargas | 100% | 2026-03-13 | 2026-03-31 | 19
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]